## UROLOGY WORKING
Category | Title | Description | Lead | Due Date | Current Update | RAG
Regional with oversight via MCN Advisory Board | eMDT Digital System | Continue to support the development and implementation of the eMDT system for urological cancers across the WoSCAN region. | MCN Clinical Lead MCN Manager MCN Members | Ongoing | Included in overarching regional delivery plan.
Regional with oversight via MCN Advisory Board | Prostate Cancer Digital Follow Up (DFUP) in patients treated with radical radiotherapy or radical prostatectomy | Continue to collaborate with NHS NSS and local clinical and ehealth teams to support implementation of DFUP and associated pathway updates in NHSAA, NHSGGC, NHSFV and NHSLAN. Provide quarterly status reports to Scottish Government. Continue to provide support and guidance to the DFUP clinical teams as enrolment to the digital pathway grows. | MCN Clinical Lead MCN Manager National eHealth Local eHealth | Ongoing | Included in overarching regional delivery plan.
|  | Evaluation of patient experience: review and undertake analysis of patient reported feedback via the digital system. Report findings to SG via the Regional Steering Group. Evaluation and analysis of staff experience of DFUP. Report findings to SG via the Regional Steering Group. Consider any pathway adjustments/updates required in response to analysis of feedback. | MCN Clinical Lead MCN Manager NHSNSS Support Board Clinical Teams | Ongoing | Included in overarching regional delivery plan.
|  | Consider findings from HIS SPOC scalability assessment in context of current project scope and future possibilities. Scope areas for future expansion, funding and resource allocation permitting. | MCN Clinical Lead MCN Manager | Ongoing | Included in overarching regional delivery plan.
Regional with oversight via Advisory Board | Robotic Assisted Surgery (RAS) Pathways and Outcomes | Support Regional Planning models of delivery of robotic assisted surgery. Robotic Assisted Laparoscopic Prostatectomy Robotic Assisted Laparoscopic Cystectomy | MCN Clinical Lead MCN Manager MCN Members | Ongoing | Included in overarching regional delivery plan.
Regional with oversight via Advisory Board | Prostate Cancer ePROMS | Continue to support the implementation of prostate cancer ePROMS process for patients treated with radical radiotherapy or radical brachytherapy patients based on the system implemented for radical prostatectomy and reported Nationally via prostate cancer QPI 8. | MCN Manager | Ongoing | Included in overarching regional delivery plan.
Regional with oversight via Advisory Board | Oncology Service Review (Urology Target Model) | Support Regional Planning workstream for identification of an efficient and resilient target operating model to address immediate, medium, and long term oncology service pressures to reach agreement on a plan for redesign and improvement of services across the WoS. | MCN Clinical Lead MCN Manager MCN Members Projects and Planning Manager | Ongoing | Included in overarching regional delivery plan.
Advisory Board | WoSCAN Clinical Management Guidelines (CMGs) | Maintain the suite of Urology CMGs. Update in line with regular review schedule and/or SMC/NCMAG approvals. Penile Cancer CMG Upper Urinary Tract Urothelial Carcinoma | MCN Clinical Lead MCN Manager Uro-oncology Lead | Ongoing August 2025 June 2025 | Included in overarching regional delivery plan.
National | Scottish Cancer Network Clinical Management Pathways (CMPs) | Collaborate with the Scottish Cancer Network (SCN) to transition from WoSCAN regional specific clinical management guidelines (CMGs) to a national clinical management pathway (CMP) for prostate cancer. | MCN Clinical Lead MCN Manager MCN Representatives | In line with SCN CMP timeline. | Included in overarching regional delivery plan.
Advisory Board | WoSCAN Clinical Guidance Documents (CGDs) | Update Bladder cancer follow up CGD Develop regional consensus for the routine PSA schedule and repeat/additional testing criteria for prostate cancer watchful waiting to supplement the information in the national CMP. | MCN Manager MCN Representatives | 2025-06-01
Advisory Board | Service Configuration Maps | Update annually in line with QPI report publication schedule. | MCN Manager | In line with QPI report publication schedule
Advisory Board | MCN Education Event | Development of a focused programme for the event, addressing relevant key issues. | MCN Clinical Lead MCN Manager | 2025-09-01
Scope appetite for and feasibility of WoSCAN hosting a national education event.
Advisory Board | Clinical Audit Data | Review individual tumour specific QPI audit findings to identify variation in practice and highlight exceptions. | MCN Clinical Lead MCN Manager WoSCAN Information Team | In line with regional audit report publication schedule. Prostate Renal/RPU Bladder Testicular
Governance review and Interrogation of QPI exceptions.
Input to the production of individual urological cancers tumour specific Annual Clinical Audit Reports.
Monitor and ensure progress of improvement action plans.
National with oversight via Advisory Board | Renal QPI Formal Review | Engage with national formal review process. Engage with MCN and collate regional response on behalf of WoSCAN. Consider development of appropriate QPIs for RPU cancer for inclusion in the renal QPI dataset. | MCN Clinical Lead MCN Manager Regional Representatives | To commence 2025 in line with national schedule. | 3 KOMs within RPU regional dataset which could potentially be included within the renal QPI dataset.

## UROLOGY REGIONAL
Category | Chapter | Title | Description | Current Update | Milestone 1 April/May/June 25 | Milestone 2 July/Aug/Sept 25 | Milestone 3 Oct/Nov/Dec 25 | Milestone 4 Jan/Feb/Mar 26
Innovation | Data collection and Intelligence | MDT Digital System | Continue to support the development and implementation of the eMDT system for Urological Cancer MDTs across the WoSCAN region. | Urology module in early UAT with MCN Manager and Clinical Lead. Wider UAT with a small group of clinicians planned in Q2 2025. Delay due to concurrent development and implementation of Lung and HPB modules and limited resource within eMDT Team. | Progress updates communicated via MDT IPB and MDT Steering Group meetings. Ongoing UAT with representatives from various specialties across the MDTs. | Progress updates communicated via MDT IPB and MDT Steering Group meetings. Key Stakeholder engagement prior to implementation. Define and agree outputs/reports to be generated from the MDT system. | Progress updates communicated via MDT IPB and MDT Steering Group meetings. Implementation of MDT system across WoSCAN Urological Cancer MDTs. | Progress updates communicated via MDT IPB and MDT Steering Group meetings. Evaluate impact of new MDT system.
Innovation | Person Centred Care for All | Prostate Cancer Digital Follow Up (DFUP) in patients treated with radical radiotherapy or radical prostatectomy. | Continue to collaborate with NHS NSS and local clinical and ehealth teams to support implementation of DFUP and associated pathway updates in NHSAA, NHSGGC, NHSFV and NHSLAN. | All WoSCAN boards are now utilising the live pathway. Patient feedback analysis to be undertaken in Q2 2025. Staff user evaluation to be undertaken in Q1 2025. SLWG, with representation from WoSCAN and NHS NSS, to be established to progress remote pathway updates in regards to inclusion of automated phlebotomy reminders. | Maintain project oversight and momentum via Regional Steering Group meeting forum. Continue to engage with NHS NSS and regional boards on identification of and implementation of pathway developments. Evaluation of staff user and patient experience. Provide requested quarterly SPoC progress updates to Scottish Government. Continue to provide support and guidance to the DFUP clinical teams as enrolment to the digital pathway grows. | Maintain project oversight and momentum via Regional Steering Group meeting forum. Continue to engage with NHS NSS and regional boards on identification of and implementation of pathway developments. Evaluation of patient experience. Provide requested quarterly SPoC progress updates to Scottish Government. Continue to provide support and guidance to the DFUP clinical teams as enrolment to the digital pathway grows. | Maintain project oversight and momentum via Regional Steering Group meeting forum. Continue to engage with NHS NSS and regional boards on identification of and implementation of pathway developments. Evaluation of patient experience. Provide requested quarterly SPoC progress updates to Scottish Government. Continue to provide support and guidance to the DFUP clinical teams as enrolment to the digital pathway grows. | Maintain project oversight and momentum via Regional Steering Group meeting forum. Continue to engage with NHS NSS and regional boards on identification of and implementation of pathway developments. Re-evaluation of staff user experience. Provide requested quarterly SPoC progress updates to Scottish Government. Continue to provide support and guidance to the DFUP clinical teams as enrolment to the digital pathway grows. Consider options for wider roll out to other prostate cancer groups and tumour groups pending additional funding from Scottish Government.
Innovation | Safe, Realistic & Effective Treatment | Robotic Assisted Surgery (RAS) Pathways and Outcomes | Support Regional Planning models for delivery of robotic assisted surgery Robotic Assisted Laparoscopic Prostatectomy (RALP) Robotic Assisted Laparoscopic Cystectomy (RALC) | Part of ongoing RAS review led by Regional Planning. | As per overarching workplan. | As per overarching workplan. | As per overarching workplan. | As per overarching workplan.
Innovation | Data collection and Intelligence | Prostate Cancer ePROMS | Continue to support the implementation of prostate cancer ePROMS process for patients treated with radical radiotherapy or radical brachytherapy based on the system already implemented for radical prostatectomy patients and reported Nationally via prostate cancer QPI 8. | Process formalised with BWoSCC Urology Team and awaiting enrolment of patients. Awaiting feedback from BWoSCC Lead Nurse on the agreed enrolment process for Lanarkshire BWoSCC patients. | Assess compliance via WoSCAN quarterly RAS audit. | Assess compliance via WoSCAN quarterly RAS audit. Assess compliance via WoSCAN clinical audit data. | Assess compliance via WoSCAN quarterly RAS audit. | Assess compliance via WoSCAN quarterly RAS audit.
Once for Scotland | Governance | Scottish Cancer Network Clinical Management Pathways (CMPs) | Collaborate with the Scottish Cancer Network (SCN) to transition from WoSCAN regional specific clinical management guidelines (CMGs) to a national clinical management pathway (CMP) for prostate cancer. | Publication of Prostate Cancer CMP is anticipated early Q2 2025. | Archive existing prostate CMGs following publication of the Prostate Cancer CMP. Engage with the SCN CMP Editorial Group for any CMP updates. | Engage with the SCN CMP Editorial Group for any CMP updates. | Engage with the SCN CMP Editorial Group for any CMP updates. | Engage with the SCN CMP Editorial Group for any CMP updates.